## Open Questions
Job 2250823 - Austin Stone
6 open - ready to ship when this is 0 and every unit and filter is accounted for
Status | Question | Who knows
Open | Which RTUs got which size? 4 RTUs (1A,2A,1C,2C) need 48 of 2", only 36 ordered; 12 extra 4" ordered. Did any of those four get filters yet, and what size? | Angel / techs
Open | Are the 12 extra 4" filters (8 of 20x25x4, 4 of 20x20x4) RTU-2B-2's? When will 2B-2 be done? | Angel
Open | For each order, which units did the filters go to (fills the 'Units it went to' column)? | Techs
Open | AHU-1 and ERV-1: are the sizes right (20x24 vs the RTUs' 20x25) and are they still not replaced? | Angel / PM
Open | Project phase for this job (blank for now). | Angel
Open | Sets 3 (final, MERV 13) and attic stock: any quantity or timing planned? | Jordan (PM)
Answered | PO numbers: 380118 for the 12-filter order, 382244 for the 60-filter order. | Angel
Answered | Order 1 date is 9/22/2026 (not 9/25). | Angel
Answered | Both orders are Set 2, MERV 8. | Angel