## Open Questions
Job 2250823 - Austin Stone
4 open - ready to ship when this is 0 and every unit and filter is accounted for
Status | Question | Who knows
Open | Possible size substitution on set 2: 4" filters may have been installed in some 2" RTUs (1A, 2A, 1C, 2C). 48 of 2" needed, 36 ordered; 12 extra 4" ordered. Which units got which? (Angel's theory, unconfirmed) | Angel / techs
Open | Are the 12 extra 4" filters (8 of 20x25x4, 4 of 20x20x4) RTU-2B-2's, or were they used as substitutes? When will 2B-2 be done? | Angel
Open | For each order, which units did the filters go to (fills the 'Units it went to' column)? | Techs
Open | AHU-1 and ERV-1 are not replaced yet. Are their sizes right (20x24 vs the RTUs' 20x25)? Set 3 must match the spec size exactly. | Angel / PM
Answered | Phase: none right now. Added scope may come as a phase on this job number or a new job number; jobs are always separated by job number. | Angel
Answered | Attic stock: none planned. The PM can add it at any time (MERV 13). | Angel
Answered | AHU-1 and ERV-1 not replaced yet. | Angel
Answered | PO numbers: 380118 for the 12-filter order, 382244 for the 60-filter order. | Angel
Answered | Order 1 date is 9/22/2026 (not 9/25). | Angel
Answered | Both orders are Set 2, MERV 8. | Angel