## Order Log
Job number | 2250823
Project name | Austin Stone
Phase | None (single phase for now)
Airco PM | Jordan
Ordered by | Angel Leon
Order date | Filter set (1/2/3/Attic) | Vendor | Vendor SO # | Our PO # | MERV | Order total price | Size | QTY | Unit price | Line total | Units it went to | Delivery | Notes
2026-09-22 | 2 | Tex Air Austin | 766028 | 380118 | 8 | 98.24 | 20x25x4 | 8 | 8.55 |  |  | Customer pickup | Urgent, units unknown at time of order.
2026-09-22 | 2 | Tex Air Austin | 766028 | 380118 | 8 |  | 20x20x4 | 4 | 7.46
2026-10-07 | 2 | Tex Air Austin | 770738 | 382244 | 8 | 368.44 | 20x25x4 | 16 | 8.55 |  |  | Delivered 2026-10-09 | Units unknown at time of order.
2026-10-07 | 2 | Tex Air Austin | 770738 | 382244 | 8 |  | 20x25x2 | 24 | 4.83
2026-10-07 | 2 | Tex Air Austin | 770738 | 382244 | 8 |  | 20x20x4 | 8 | 7.46
2026-10-07 | 2 | Tex Air Austin | 770738 | 382244 | 8 |  | 20x20x2 | 12 | 4.67

## Needed vs Ordered
Size | Ordered (all orders) | Needed - units replaced | Left over (+) / Short (-) | Still needed - units not yet replaced
16x20x4 |  | 0 |  | 2
16x24x2 |  | 0 |  | 2
20x20x2 |  | 16 |  | 0
20x20x4 |  | 8 |  | 6
20x24x2 |  | 0 |  | 2
20x24x4 |  | 0 |  | 6
20x25x2 |  | 32 |  | 0
20x25x4 |  | 16 |  | 8