## Open Questions
OPEN QUESTIONS
Job number | 2250823
Project name | Austin Stone
Airco PM | Jordan
4 open - ready to send when this is 0 and every unit and filter is accounted for
Status | Question | Who knows
Open | All 7 RTUs need 84 filters, only 72 ordered: one RTU's worth (12) short overall. Either 1 of the 2" RTUs (1A, 2A, 1C, 2C) still needs 2" (8 of 20x25x2 + 4 of 20x20x2), or a 2" unit got 4" and RTU-2B-1 will be short on 4". Which units got what size? | Angel / techs
Open | For each order, which units did the filters go to (fills the 'Units it went to' column)? | Techs
Open | When will RTU-2B-1 be started? The extra 12 4" filters ordered are on hand for it unless they were used as substitutes. | Angel
Open | AHU-1 and ERV-1 are not replaced yet. Are their sizes right (20x24 vs the RTUs' 20x25)? Set 3 must match the spec size exactly. | Angel / PM
Answered | RTU-2B-1 (not 2B-2) is the one RTU not started up yet. 6 of 7 RTUs replaced. | Angel
Answered | Phase: none right now. Added scope may come as a phase on this job number or a new job number; jobs are always separated by job number. | Angel
Answered | Attic stock: none planned. The PM can add it at any time (MERV 13). | Angel
Answered | AHU-1 and ERV-1 not replaced yet. | Angel
Answered | PO numbers: 380118 for the 12-filter order, 382244 for the 60-filter order. | Angel
Answered | Order 1 date is 9/22/2026 (not 9/25). | Angel
Answered | Both orders are Set 2, MERV 8. | Angel